## Sheet1
Tasks | Weeks
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
| 19 - 25 Jan | 26 - 1 Feb | 2 - 8 Feb | 9 - 15 Feb | 16 - 22 Feb | 23 - 1 Mar | 2 - 8 Mar | 9 - 15 Mar | 16 - 22 Mar | 23 - 29 Mar | 30 - 5 Apr | 6 - 12 Apr | 13 - 19 Apr | 20 - 26 Apr | 27 - 3 May
Modelling Virtual Environment: | bar: Weeks Week 1 to Weeks Week 4
- Full-Flat State Environment | bar: Weeks Week 1
- Flat-Textured State | bar: Weeks Week 2
- Depth-Textured State | bar: Weeks Week 3
- Rich State | bar: Weeks Week 3 to Weeks Week 4
Implementing Controls: | bar: Weeks Week 2 to Weeks Week 5
- Manipulation Implementation | bar: Weeks Week 3
- Interface Implementation (HUD) | bar: Weeks Week 3
- Integrating Wii Remote Controller | bar: Weeks Week 4
- Integrating Oculus Rifft DK2 | bar: Weeks Week 4 to Weeks Week 5
Implementing Practice Mode | bar: Weeks Week 5
Testing and Final Enhancement | bar: Weeks Week 5 to Weeks Week 6
Carry Out Experiment | bar: Weeks Week 7 to Weeks Week 8
Reports:
- Third Progress Report | bar: Weeks Week 5
- Fourth Progress Report | bar: Weeks Week 8
- Final Project Report | bar: Weeks Week 9 to Weeks Week 13
Oral Examination | bar: Weeks Week 14
*** HOLIDAY *** | bar: Weeks Week 9 to Weeks Week 13